## Bugs
ID | Function name | Problem summary | How to reproduce it | Severity | Reported by | Comment
01 | Tìm kiếm sản phẩm | A product with new price > old price still has "Offer" tag | 1. Admin add a product with new price > old price 2. Search for that product in Product Listing page | Medium | Tung
02 | Tìm kiếm sản phẩm | Product with new price > old price has cropped "Add To Cart" button | 1. Admin add a product with new price > old price 2. Go to that product info page | Cosmetic | Tung
03 | Gửi thông tin liên hệ | User message to admin cannot be retrieved in app | 1. Leave a mesage at the Contact page 2. Admin look for where user messages are saved | Serious | Tung
04 | Gửi thông tin liên hệ | User message is also not saved in database | 1. Leave a mesage at the Contact page 2. Look for a table that store user messages in SQL database | Serious | Tung
05 | Gửi thông tin liên hệ | After submitting a message, "Success" green text remains for later messages | 1. Submit a message successfully 2. Submit another message right after, but enter wrong captcha | Cosmetic | Tung
06 | Quản lý thông tin tài khoản | Forget Password scenario lead to Error page | 1. Perform Forget Password 2. Submitting the security answer | Serious | Tung
07 | Quản lý thông tin tài khoản | Cannot log in after the failed Forget Password scenario | 1. Log in after failed Forget Password scenario | Fatal | Tung
08 | Quản lý thông tin tài khoản | Make some users admin using SQL database then go to app to change password of any account, a select box will pop up for you to select among these admin names | 1. Make some accounts admin using SQL database 2. Log in to app as any user, and change password | Cosmetic | Tung
09 | Quản lý thông tin tài khoản | The profile picture is always blank | 1. Browse an image to upload 2. try to update the profile picture | Medium | Tung
10 | Quản lý thông tin tài khoản | Click "Shop Now" when in My Account page return Error page | 1. Click "Shop Now" while in My Account page | Medium | Tung
11 | Quản lý thông tin tài khoản | Click "Shop Now" when in Delivery Address page return Error page | 1. Click "Shop Now" when in Delivery Address page | Medium | Tung
12 | Quản lý thông tin tài khoản | Click "Shop Now" when in My Orders page return Error page | 1. Click "Shop Now" when in My Orders page | Medium | Tung
13 | Đặt mua hàng | Click "Shop Now" when in Successful Order page return Error page | 1. Click "Shop Now" when in Successful Order page | Medium | Tung
14 | Đặt mua hàng | Enter non-numeric character in product quantity in cart return Error page | 1. Enter non-numeric character in product quantity in cart | Medium | Tung
15 | Đặt mua hàng | The number next to the icon cart can be negative | 1. Enter negative number in quantity of products in cart | Cosmetic | Tung
16 | Đặt mua hàng | Order including negative product quantity is accepted if total price is positive | 1. Set products quantity in cart using both positive/negative numbers 2. Ensure the total price is positive and Checkout | Serious | Tung
17 | Quản lý tài khoản người dùng | Cannot delete account created in app, even newly created w/o transaction yet | 1. Create a new account the newly created account 2. Log in as admin after and try to delete the | Serious | Tung
18 | Quản lý tài khoản người dùng | Cannot filter the list of Accounts in admin page, as per requirement | 1. Filter for the list of accounts in admin page is not implemented | Serious | Tung
19 | Quản lý đơn đặt hàng | Cannot filter the list of Orders in admin page, as per requirement | 1. Filter for the list of orders in admin page is not implemented | Serious | Tung
20 | Upload File < 5s | Average upload time when heavy-load (40 users) is 29s | 1. Using JMeter to measure | Medium | Tung
21 | Font chữ Unicode UTF-8 | Create account with UTF-8 emoji characters then log out take down the system | 1. Create an account using UTF-8 emoji characters in username 2. Login successfully 3. Then log out and the system crash, recoverable only by purging db | Fatal | Tung
22 | Money: $ 000,000.00 | Price format is without middle commas separating every 3 digits | 1. Adding to cart 1000 Channa item to get the total price as $8099.00 | Cosmetic | Tung
23 | Login | Accept incorrect username with all uppercase letters | 1. Login with username with all letters in uppercase, same password. 2. Can still login | Serious | Tri
24 | Login | Accept incorrect username with mixed case letters | 1. Login with username with letters with random case, same password. 2. Can still login | Serious | Tri
25 | Login | Accept incorrect username with added space at the end | 1. Login with username with an added space at the end, same password. 2. Can still login | Serious | Tri
26 | Login | Accept incorrect username with added space at the start | 1. Login with username with an added space at the start, same password. 2. Can still login | Serious | Tri
27 | Search | Choosing to show all items in one page, when no product matches search term, produces error | 1. Search for a search term that matches no product, like "qwe". 2. In the result page, select "All" in the menu. 3. Error message will be displayed | Medium | Tri

## Defect Severity
Defect Severity | Weight (Trọng số) | Mô tả
Fatal | 10 | Lỗi đặc biệt nghiêm trọng làm sụp hệ thống, không thể phục hồi dữ liệu
Serious | 5 | Lỗi làm chức năng chính của hệ thống không thể thực thi hoặc thực thi không đúng. Vd. Người dùng có thể thực hiện chức năng mà không cần được phân quyền
Medium | 3 | Lỗi làm chức năng phụ của hệ thống không thể thực thi hoặc thực thi không đúng. Vd. Hệ thống thực thi không đúng với dữ liệu không hợp lệ, giá trị biên hoặc chạy chậm
Cosmetic | 1 | Lỗi không ảnh hưởng đến chức năng của hệ thống. VD. Lỗi giao diện sai thứ tự Tab, default focus, short key…

## Examples
ID | Function name | Problem summary | How to reproduce it | Severity | Reported by | Comment
01 | Login as admin | Login with blank User name not display error | 1. Enter User Name : " " 2.Enter Password : "abcd" 3. Click "Ok" button | Cosmetic | TDHoang
02 | Login as end user | Login with blank User name not display error | 1. Enter User Name : " " 2.Enter Password : "abcd" 3. Click "Ok" button | Cosmetic | TDHoang